## Agile Plan
ACME ROBOTICS
| PROJECT NAME | Human Detection and Motion Tracking |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE | Real-time human detection and Tracking Software for Indoor robot
| PROJECT MANAGER | Vyshnav Achuthan , Surya Chippudi, Kiran Patil |  |  | 2023-10-10 | 2023-10-31 | 20% | SCOPE STATEMENT | A real-time detection using state of the art architecture and also track the motion of the object identified
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
No | SPRINT 1 | Framework Design and Documentation | ALL |  | 2023-10-10 | 2023-10-17 | 8
No | Proposoal Documentation | Work on setting up the problem statement and complete the statement | Kiran Patil |  | 2023-10-10 | 2023-10-17 | 8 | Complete
No | Setup Github Repo and Boilerplate | Work on setting up the repository and create the boiler plate | Vyshnav Achuthan |  | 2023-10-10 | 2023-10-17 | 8 | Complete
No | Create UML and Activity Diagrams | Work on the creation of UML and include activity diagram of the baseline | Vyshnav Achuthan |  | 2023-10-10 | 2023-10-17 | 8 | Complete
No | Create initial Design and Quad Chart | Work on creating an initial design and prepare quad chart | Surya |  | 2023-10-10 | 2023-10-17 | 8 | Complete | Need to add stub for next sprint – Carryforward
No | SPRINT 2 | Implementation of Initial Framework | ALL |  | 2023-10-17 | 2023-10-24 | 8 | In Progress
No | Feature 4
No | Feature 5
No | Feature 6
No | SPRINT 3
No | Feature 7
No | Feature 8
No | Feature 9
TDD Enactment
Task Code | Task Description
Formulas:
START DATE = MIN([START DATE, row below]:G9)
END DATE = MAX([END DATE, row below]:H9)

## Product Backlog
Acme Robotics
Product Backlog | [5 empty] | Use index colors to show revisions on task time
Unique ID | Task | Sprint | Estimated time (minutes) | Time after Iteration 1 | Time after Iteration 2 | Index | Information
Target Time
1 | Design and Documentation |  | 865 | 955 | 0 |  | Revised Target Time
1.11 | Create repo and get license | 1 | 10 | 10 |  |  | Actual Time Taken
1.12 | Document the report | 1 | 300 | 280 |  |  | New Task Added
1.13 | Updated UML diagram | 1 | 60 | 90
1.14 | Create 3 minute video explaining phase 1 | 1 | 60 | 60
1.15 | Install dependencies and check version | 1 | 60 | 100
1.16 | Create AIP Sheet | 1 | 15 | 15
1.17 | Research on ByteTrack and YOLOv3 | 1 | 360 | 400
2 | Implementation |  | 0 | 0 | 0
| Remaining effort |  |  | -90 | 0
| Total effort time |  | 865 | 955 | 0

## Iteration Backlog1
ACME ROBOTICS
Iteration Backlog 1
Unique ID | Task | Target time (minutes) | Actual Time | Status | Completed
In Progress
1 | Plan and Design | 1165 | 1165 | Completed | To Do
1.11 | Create GitHub Repository | 10 | 5 | Completed
1.12 | Create Project Proposal | 320 | 380 | Completed
1.13 | Research on YOLOV3 | 360 | 400 | Completed
1.14 | Install Pytorch | 120 | 45 | Completed
1.14 | Check OpenCV 3.4 | 10 | 30 | Completed
1.14 | Add .travis.yml file with dependencies | 20 | 20 | Completed
1.15 | Add detailed Readme.md | 60 | 40 | Completed
1.15 | Create CmakeLists.txt file | 20 | 20 | Completed
1.16 | Update AIP Sheet | 100 | 90 | Completed
1.12 | Update Activity Diagram | 100 | 90 | Completed
1.12 | Update Readme and Quad-chart | 30 | 30 | Completed
1.18 | Git branching in the repository | 15 | 15 | Completed

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold